## DW Retrofit
% Complete | Task Name | Duration | Start | Finish | Comments
100% | POC - Data Lineage | 49 | 2019-11-25 | 2020-01-12
100% | Enviornment/Infra Setup | 9 | 2019-11-25 | 2019-12-03
100% | Acquiring Windows VM Server with required specs for POC | 3 | 2019-11-25 | 2019-11-27
100% | Oracle Client Setup VM Server | 1 | 2019-11-28 | 2019-11-28
100% | Port Opening activity across enviornments | 5 | 2019-11-28 | 2019-12-02
100% | Acquiring external storage drive for backup and file sharing | 5 | 2019-11-29 | 2019-12-03
100% | Application Setup | 6 | 2019-12-05 | 2019-12-10
100% | ASG DI - Rochade Server Installation | 2 | 2019-12-05 | 2019-12-06
100% | ASG DI - Metability Installation | 1 | 2019-12-07 | 2019-12-07
100% | ASG DI - Oracle Scanner Installation and configuration | 2 | 2019-12-08 | 2019-12-09
100% | ASG DI - Recon Toolkit Installation | 2 | 2019-12-09 | 2019-12-10
100% | ASG DI - Scanner read access to all database metadata and objects | 2 | 2019-12-09 | 2019-12-10
100% | Development | 33 | 2019-12-11 | 2020-01-12
100% | Oracle Scanner config changes to read database tables metadata, packages, procedures and then loading them to ASG Stage | 2 | 2019-12-11 | 2019-12-12
100% | Filtering Out relevant Critical data elements out of metadata information and building correlation/ lineage | 1 | 2020-01-05 | 2020-01-05 | There is a gap in between as vendors were on annual leave
100% | Front End lineage tracking w.r.t. critical data elements | 2 | 2020-01-06 | 2020-01-07
100% | Creation of Business Glossary | 4 | 2020-01-08 | 2020-01-11
100% | Creating comparison snapshots to identify changes in lineage flow | 1 | 2020-01-12 | 2020-01-12
Next Steps
0% | Presenting Business Usecase to FAB Management
0% | Fixing Metadata Management Solution Toolkit
0% | Placing it into our SDLC process
0% | Production Setup
0% | Acquiring Windows VM Server with required specs for POC
0% | Oracle Client Setup VM Server
0% | Port Opening activity across enviornments
0% | Acquiring external storage drive for backup and file sharing
0% | Application Setup
0% | ASG DI - Rochade Server Installation
0% | ASG DI - Metability Installation
0% | ASG DI - Oracle Scanner Installation and configuration
0% | ASG DI - Recon Toolkit Installation
0% | ASG DI - Scanner read access to all database metadata and objects
0% | Development - Phase 1
0% | Identify Data Source- Alchemy, SUMX, etc.
0% | Identify critical data elements for the source identified
0% | Get read only access for a master user on all system managed tables in the database
0% | Oracle Scanner config setup to read database tables metadata, packages, procedures and then loading them to ASG Stage
0% | Creating Business Glossary for the process
0% | Mapping related fields w.r.t. Business Glossary
0% | Creating snapshots and identifying changes in lineage
0% | Testing - Phase 1
0% | Testing end to end lineage getting captured properly for critical data elements
0% | Testing forward data lineage
0% | Testing comparison snapshots able to capture transformation changes properly
0% | Training
0% | Training BAU how to use the solution
0% | Documentation and implementation of process to follow going forward for any change implementation in production
RESOURCE Requirement
Business Spoc to help us creating and maintaining Business Glossary for respective process as we proceed
1 vendor resource for assistance and support during the entire setup and knowledge transfer
1 ETL resource onsite to develop and train BAU team on the tool
1 ETL offshore resource to support the development

## Finance - Big Data
% Complete | Task Name | Duration | Start | Finish | Comments (if any)
78% | POC - SUMX Ingestion to Hadoop | 62 | 2019-10-20 | 2020-01-26
85% | Development | 54 | 2019-10-20 | 2020-01-21
100% | Writing all onesumx dimensions in hadoop | 3 | 2019-10-20 | 2019-10-22
100% | Writing files for last 3 Month ends and 2018 year end data in hadoop | 6 | 2019-10-23 | 2019-10-28
100% | Enviornment setup by moving required jars to enhance spark processing | 2 | 2019-10-29 | 2019-10-30
100% | Creating alchemy onesumx data model in hadoop- creating external tables with write compression | 6 | 2019-10-31 | 2019-11-05
100% | Develop scala package to process onesumx outbound balance file and create Base agg on spark | 7 | 2019-11-06 | 2019-11-12
100% | Develop scala package to process onesumx outbound balance file and create base Customer agg on spark | 6 | 2019-11-13 | 2019-11-18
100% | Develop scala package to process onesumx outbound balance file and create base GL agg on spark | 12 | 2019-11-19 | 2019-11-30
100% | Log file to monitor all the loads and failure if any | 2 | 2019-12-01 | 2019-12-02
100% | Script to refresh Hive/Impala metadata and partitions post load completion | 1 | 2019-12-03 | 2019-12-03
100% | Master Shell script to package these loads | 2 | 2019-12-04 | 2019-12-05
30% | Power BI conection to kerberose hadoop setup | 6 | 2020-01-15 | 2020-01-20 | There is a gap as team was busy finishing KPI dashboard deliveries to Business
0% | Power BI cube refresh with impala tables | 1 | 2020-01-21 | 2020-01-21
52% | Testing | 8 | 2019-12-08 | 2020-01-26
70% | Balance recon queries against each measure - base agg with alchemy | 3 | 2019-12-08 | 2019-12-10
70% | Balance recon queries against each measure - customer agg with alchemy | 1 | 2019-12-11 | 2019-12-11
70% | Balance recon against each measure - GL agg with alchemy | 4 | 2019-12-12 | 2019-12-15
0% | Power BI cubes recon from impala against alchemy | 0 | 2020-01-22 | 2020-01-26
0% | Production - SUMX Daily Load and MI Reporting | 64 | 2020-01-27 | 2020-03-31
0% | Development | 33 | 2020-01-27 | 2020-02-29
0% | Daily Production Run | 24 | 2020-01-27 | 2020-02-20
0% | Creating all onesumx dimensions in hadoop | 3 | 2020-01-27 | 2020-01-29
0% | Enviornment setup by moving required jars to enhance spark processing | 2 | 2020-01-30 | 2020-01-31
0% | Creating alchemy onesumx data model in hadoop- creating external tables with write compression | 3 | 2020-02-01 | 2020-02-03
0% | Prod Movement - scala package to process onesumx outbound balance file and create Base agg on spark | 1 | 2020-02-04 | 2020-02-04
0% | Prod Movement - Develop scala package to process onesumx outbound balance file and create base Customer agg on spark | 1 | 2020-02-05 | 2020-02-05
0% | Prod Movement - Develop scala package to process onesumx outbound balance file and create base GL agg on spark | 2 | 2020-02-06 | 2020-02-07
0% | Develop Log file tracking to monitor all the loads and failure if any | 3 | 2020-02-08 | 2020-02-10
0% | Develop Script to refresh Hive/Impala metadata and partitions post load completion | 1 | 2020-02-11 | 2020-02-11
0% | Develop Master Shell script to package these loads | 3 | 2020-02-12 | 2020-02-14
0% | Develop NIFI Job for regular job scheduling | 1 | 2020-02-15 | 2020-02-15
0% | Power BI connection to kerberose hadoop setup | 15 | 2020-02-01 | 2020-02-15 | Needs port opening, kerberose client software installation at server side and testing connectivity. Can happen in parallel.
0% | Power BI cube development and refresh with impala tables | 5 | 2020-02-16 | 2020-02-20
0% | History Load | 9 | 2020-02-21 | 2020-02-29
0% | History Load for Base Agg | 2 | 2020-02-21 | 2020-02-22
0% | History Load for Customer Agg | 3 | 2020-02-23 | 2020-02-25
0% | History Load for GL Agg | 4 | 2020-02-26 | 2020-02-29
0% | Testing - Internal IT | 16 | 2020-03-01 | 2020-03-16
0% | Balance recon against each measure - base agg with alchemy | 3 | 2020-03-01 | 2020-03-03
0% | Balance recon against each measure - customer agg with alchemy | 3 | 2020-03-04 | 2020-03-06
0% | Balance recon against each measure - GL agg with alchemy | 4 | 2020-03-07 | 2020-03-10
0% | Power BI cubes recon from impala against alchemy | 6 | 2020-03-11 | 2020-03-16
0% | Control -M file automation to move SUMX files to hadoop | 16 | 2020-03-01 | 2020-03-16 | Needs control-M job setup, development and testing to move SUMX files from SUMX prod to hadoop prod. Can work in parallel.
0% | Testing - Business UAT | 15 | 2020-03-17 | 2020-03-31
0% | Release reports to business | 15 | 2020-03-17 | 2020-03-31
0% | Production - SUMX power pivot Recon and external files consumption | 40 | 2020-03-01 | 2020-04-10
0% | Development | 26 | 2020-03-01 | 2020-03-26
0% | Discussion with SUMX Team on the power pivot recon process | 1 | 2020-03-01 | 2020-03-01
0% | Develop jobs to consume any new file to hadoop | 2 | 2020-03-02 | 2020-03-03
0% | Build existing recon queries using spark SQL and package into scala executables for ingestion | 7 | 2020-03-04 | 2020-03-10
0% | Create similar tables in impala with required partitions | 3 | 2020-03-11 | 2020-03-13
0% | History loading of any new files if required for the process | 5 | 2020-03-14 | 2020-03-18
0% | History loading of recon output (if in scope) | 5 | 2020-03-14 | 2020-03-18
0% | Load process automation depending on frequency of validation | 5 | 2020-03-19 | 2020-03-23
0% | Power BI olap cube development | 4 | 2020-03-19 | 2020-03-22
0% | Power BI report development | 4 | 2020-03-23 | 2020-03-26
0% | Testing - Internal IT | 13 | 2020-03-19 | 2020-03-31
0% | Recon output from Impala against SUMX | 5 | 2020-03-19 | 2020-03-23
0% | Power BI output against power pivot output for business consumption | 5 | 2020-03-27 | 2020-03-31
0% | Testing - Business UAT | 10 | 2020-04-01 | 2020-04-10
0% | Power BI output against power pivot output for business validation | 10 | 2020-04-01 | 2020-04-10
RESOURCE Requirement
1 hadoop developer onshore
1 hadoop developer offshore

## FCD Migration
% Complete | Task Name | Duration | Start | Finish | Comments (if any)
0% | Identifying spoc from Business and FCD Team to discuss the scope of development
0% | Getting read access to the Teradata enviornment to understand the data model in place
0% | Identifying any new source onboarding to DWH
0% | Identifying the total no. of tables in scope for migration
0% | List of power pivot reports business using from FCD if any
0% | Any external data source loading in FCD
0% | Estimate ETL development to onboard new source system
0% | Estimate ETL development to migrate FCD to alchemy
0% | Estimate Power BI development plan
0% | Estimate internal IT testing
0% | Estimate Business UAT
0% | Estimate Production Rollout
RESOURCE Requirement
2 ETL Resources onsite
1 ETL Resource offshore