## DW Retrofit
% Complete | Task Name | Duration | Start | Finish | Comments
100% | POC - Data Lineage
100% | Enviornment/Infra Setup | 8 | 2019-11-25 | 2019-12-03
100% | Acquiring Windows VM Server with required specs for POC
100% | Oracle Client Setup VM Server
100% | Port Opening activity across enviornments
100% | Acquiring external storage drive for backup and file sharing
100% | Application Setup
100% | ASG DI - Rochade Server Installation
100% | ASG DI - Metability Installation
100% | ASG DI - Oracle Scanner Installation and configuration
100% | ASG DI - Recon Toolkit Installation
100% | ASG DI - Scanner read access to all database metadata and objects
100% | Development
100% | Oracle Scanner config changes to read database tables metadata, packages, procedures and then loading them to ASG Stage
100% | Filtering Out relevant Critical data elements out of metadata information and building correlation/ lineage
100% | Front End lineage tracking w.r.t. critical data elements
100% | Creating comparison snapshots to identify changes in lineage flow
100% | Creation of Business Glossary
Next Phase
Presenting Business Usecase to FAB Management
Fixing Metadata Management Solution Toolkit
Placing it into our SDLC process
Production Setup
Acquiring Windows VM Server with required specs for POC
Oracle Client Setup VM Server
Port Opening activity across enviornments
Acquiring external storage drive for backup and file sharing
Application Setup
ASG DI - Rochade Server Installation
ASG DI - Metability Installation
ASG DI - Oracle Scanner Installation and configuration
ASG DI - Recon Toolkit Installation
ASG DI - Scanner read access to all database metadata and objects
Development - Phase 1
Identify Data Source- Alchemy, SUMX, etc.
Identify critical data elements for the source identified
Get read only access for a master user on all system managed tables in the database
Oracle Scanner config setup to read database tables metadata, packages, procedures and then loading them to ASG Stage
Creating Business Glossary for the process
Mapping related fields w.r.t. Business Glossary
Creating snapshots and identifying changes in lineage
Testing - Phase 1
Testing end to end lineage getting captured properly for critical data elements
Testing forward data lineage
Testing comparison snapshots able to capture transformation changes properly
Training
Training BAU how to use the solution
Documentation and implementation of process to follow going forward for any change implementation in production
RESOURCES
Resources
Business Spoc to help us creating and maintaining Business Glossary
1 vendor resource for assistance and support during the entire setup and knowledge transfer
1 FABIT resource to manage this

## Finance - Big Data
% Complete | Task Name | Duration | Start | Finish | Comments
100% | Application Setup | 5 | 2019-12-05 | 2019-12-10
20% | Development | 1 | 2019-12-11 | 2019-12-12
80% | Development | 3 | 2020-01-05 | 2020-01-08 | There is a gap in between as vendors were on annual leave
100% | Testing | 3 | 2020-01-09 | 2020-01-12

## Sheet2
What technology
What kind of resources
What